## Work Order
WORK ORDER SHEET (Rev.0) | [8 empty] | Department : | Production 2 |  | Foreman : | Mr.Huy
[9 empty] | Issue Date : | 2012-03-17 |  | W.Period : | 17/Mar ~ 23/Mar
[9 empty] | Doc. No : | WO-P2-5-1-W12 |  | Prepared : | Van Con Hoi
○Production Summary
Project Information |  |  |  | Target |  |  | Accumulation |  |  | This week |  |  |  | Remark
Name |  | Contract weight (kg) |  | Order quantity (kg) |  | Productivity (kg/MD) | Fabrication (Kg) | Productivity (kg/MD) | Manpower (person) | Fabrication (Kg) | Productivity (kg/MD) | Manpower (person) | Daily Man. (person)
CT0257-IVANPAH | [5 empty] | #DIV/0! | 61403.7 | 97.3117 | 631 | 18728.9326 | 178.3708 | 105 | 15
○Check List
No. | DWGNO | Rev. | Name | IDMK | QTY | UNIT | TOTALW/T | Checked by Engineer |  |  | Checked by Foreman
[8 empty] | DWG & CP | Material | Deadine | Mar/Cut | Fit-up | Welding | Inspection
1 | SD-710 | 4 | PL60 | PL60*210 | 4 | 25.7 | 102.8 | 2012-02-10 |  | 2012-03-23
2 | SD-726 | 1 | BLANK PLATE | BLK1 | 1 | 1413.1 | 1413.1 | 2012-02-10 |  | 2012-03-23
3 | SD-726 |  | BLANK PLATE | BLK2 | 1 | 1469.9 | 1469.9 | 2012-02-10 |  | 2012-03-23
4 | SD-726 |  | BLANK PLATE | BLK3 | 1 | 2075.9 | 2075.9 | 2012-02-10 | Have | 2012-03-23
5 | SD-726 |  | BLANK PLATE | BLK4 | 1 | 1413.1 | 1413.1 | 2012-02-10 | Have | 2012-03-23
6 | SD-710 | 4 | SADDLE | U3-710SBP | 1 | 1239.7 | 1239.7 | 2012-02-10 | Have | 2012-03-14 | 2012-03-11 | 2012-03-12
7 | SD-706 | 4 | TED | U3-TED2-1A | 1 | 774.7952 | 774.7952 | 2012-02-10 | Have | 2012-03-20 | 2012-03-12 | 2012-03-13
8 | SD-706 | 4 | TED | U3-TED2-1B | 1 | 861.7772 | 861.7772 | 2012-02-10 | Have | 2012-03-20 | 2012-03-12 | 2012-03-13
9 | SD-706 | 4 | TED | U3-TED2-1C | 1 | 774.7952 | 869.9772 | 2012-02-10 | Have | 2012-03-20 | 2012-03-12 | 2012-03-13
10 | SD-706 | 4 | TED | U3-TED2-3A | 1 | 2642.8054 | 2642.8054 | 2012-02-10 |  | 2012-03-30 | 2012-03-10 | 2012-03-11
11 | SD-706 | 4 | TED | U3-TED2-3B | 1 | 2924.2388 | 2924.2388 | 2012-02-10 |  | 2012-03-30 | 2012-03-10 | 2012-03-11
12 | SD-706 | 4 | TED | U3-TED2-3C | 1 | 2940.8388 | 2940.8388 | 2012-02-10 |  | 2012-03-30 | 2012-03-10 | 2012-03-11
SUB.T |  |  |  |  | 15 |  | 18728.9326
[7 empty] | #REF! |  |  | We calculate=Manpowerx6days. (Not show)
[7 empty] | #REF! |  |  | We calculate= Total weight/Total manpower. (Not show)
[8 empty] | Prepared |  | Approved |  |  | Fabricated
# 1) How to decide target productivity ?
| Budget of Labor Cost |  | Average salary | Mobilization Manpower |  | Target Productivity
| (USD) |  | (USD/day) | (Person) |  | (Kg/MD)
|  |  |  | #DIV/0! |  | #DIV/0! |  | Engineer Name |  | T.Leader Name |  |  | Foreman Name
Note on G6: Target should be decided based on budget of labor cost (refer to #1)